## Slide 1: Tay Cities Region Deal
Benefits Realisation Plan

## Slide 2: What is a Benefits Realisation Plan?
A Benefits Realisation Plan (BRP) sets out the Deal’s approach to monitoring & evaluation
It is a commitment of the Deal as set out in the Grant Offer Letter and individual Project’s Legal Agreements
Projects will report updates on their outputs, outcomes & impacts over the life of the Deal in order to monitor & evaluate the Deal’s overall commitment of:
Inclusive Growth, Carbon, Community Wealth Building & Community Benefit impacts will also be recorded

## Slide 3: What has been achieved so far?
Dr Mark Graham appointed to support PMO (13/10/21)
Dr Mark Graham introductory presentation to Joint Committee (December 2021)
Review Panel Established (28/10/21)
Close working relationship with other Deals (on-going)
BRP commitment set out in Grant Offer Letter (December 2020)
Workshops to inform definitions, Logic Chain Models & reporting template (January 2022)
BRP developed & shared with Partnership & Governments for comment (01/02/22)

## Slide 4: What next?
By June 2022, the following actions are committed to:
  Review all returned Logic Chain Models
  Begin work with all year 3 + Programmes and Projects to develop their Logic Chain Models
  Review and update the Definitions Guidance before sharing with all Programmes /Projects/Fund
  Pilot the reporting template with volunteer project(s)
  Undertake the annual review of the Implementation Plan to align it with the Benefits Realisation Plan
Reporting of Benefits to be included as part of Q2 and Q4 Quarterly Report

## Slide 5: What next?
The Benefits Realisation Plan is an on-going piece of work so the PMO will continue to discuss progress and provide updates to the Partnership
Both Governments have indicated that they are content with the principles and overall approach to monitoring & evaluation. They have commended it for being a good, simple example for other Deals
The UK Government have approved the Plan. The Scottish Government have requested minor changes for clarity. They confirmed on 10th March that they were happy to approve the Plan with further updates to be actioned by the PMO by the end of April. It will then be published on the Tay Cities website
The Joint Committee is asked to approved the Plan

## Slide 6: @taycities www.taycities.co.uk lauren.hollas@taycities.co.uk